## Sheet1
Workflows | Existing Reusable Workflows | Customisation needed | Effort in hours | Comments | Complete status
Initialise all settings | Yes | Not Required
Close Edge Browser | Yes | Not Required
Prompt user for input file | Yes | Yes | 4 | To adjust form display size To add additional configurable parameters | Done
Read input file | Yes | Yes | 4 | To rename variables
Validate input file | Yes | Yes | 8 | To validate data in columns - Invoice amount, Invoice Date, GL Date &Terms date
Prompt user for login credentials | No | NA | 4
Login to Oracle ERP | Yes | Yes | 8 | To add login success validation To add retry logic for login failure
Navigate to Invoices | No | NA | 4 | To add logic for DOL payables manager validation
Handle security warnings | Yes | Yes | 16 | To add logic to handle all prompts dynamically
Enter Invoice details in Master Block | No | NA | 24 | 1. To enter 12 fields (Type, PO number, Supplier site, Invoice date, Invoice number, Invoice amount, GL Date, Payment currency, Terms date, Terms, Payment method, Pay Group) 2. To validate 10 fields for exceptions (Type, PO number, Supplier site, Invoice date, Invoice number, GL Date, Payment currency, Terms, Payment method, Pay Group) 3. To add status in excel for relevant exceptions 4. To add retry logic wherever necessary (TBD)
Enter Invoice details in Detail Block | No | NA | 24 | 1. Find PO window -3 UI interactions, 1 validation 2. Match to PO window- 4 UI interactions, 1 validation 3. Invoice Workbench- 1 UI interaction 4. Invoice Actions- 2 UI interactions 5. Invoice Workbench-2 validations 6. To add status in excel for relevant exceptions 7. To add retry logic wherever necessary (TBD)
Update status in Output file | Yes | Yes | 4 | To update Bot status and Bot comments along with exceptions
Send mail to SME | Yes | Yes | 4 | To remove message box logic
Logout Oracle ERP | Yes | Not Required
Custom RE Framework | Yes | Yes | 4 | To remove Journal references

## Sheet2
Workflows | Existing Reusable Workflows | Customisation needed | Effort in hours | Status
|  |  |  | Development | Unit Testing | Peer Review | Start Date | End Date
Initialise all settings | Yes | Not Required
Close Edge Browser | Yes | Not Required
Prompt user for input file | Yes | Yes | 4 | Done | Done | Done | 2022-05-05 | 2022-05-05
Read input file | Yes | Yes | 4 | Done | Done | Done | 2022-05-06 | 2022-05-07
Validate input file | Yes | Yes | 8 | Done | Done | Done | 2022-05-09 | 2022-05-10
Get Unique Invoices List | Yes | Yes | 4 | Done | Done | Done | 2022-05-09 | 2022-05-11
Prompt user for login credentials | No | NA | 4 | Done | Done | Done | 2022-05-06 | 2022-05-16
Launch Oracle ERP | Yes | Yes | 8 | Done | Done | Done | 2022-05-09 | 2022-05-16
Login to Oracle ERP | Yes | Yes | 8 | Done | Done | Done | 2022-05-06 | 2022-05-16
Navigate to Invoices | No | NA | 4 | Done | Done | Done | 2022-05-10 | 2022-05-10
Handle security warnings | Yes | Yes | 16 | Done | Done | Done | 2022-05-15 | 2022-05-16
Enter Invoice details in Master Block | No | NA | 24 | inprogress |  |  | 2022-05-13
Enter Invoice details in Detail Block | No | NA | 24 | inprogress |  |  | 2022-05-13
Update status in Output file | Yes | Yes | 4
Send mail to SME | Yes | Yes | 4 | Done | Done | Done | 2022-05-16 | 2022-05-16
Logout Oracle ERP | Yes | Not Required |  | Done | Done | Done | 2022-05-10 | 2022-05-11
Custom RE Framework | Yes | Yes | 4 | Done | Done | Done | 2022-05-09 | 2022-05-09
Start Date | 2022-05-05
End Date | 05-20-2022

## Sheet3
Workflows | Existing Reusable Workflows | Customisation needed | Effort in hours | Input Args | Output Args | Status |  |  | Start Date | End Date | Checklist | [8 empty] | Comments
[6 empty] | Development | Unit Testing | Peer Review |  |  | Variables NC | Variables scope | Args NC | Args Direction | Unused Variables/Args/Keys | Annotations | Logs | Rename activities | Hardcoded values
Initialise all settings | Yes | Not Required |  | 1. in_ConfigFile : String 2. in_ConfigSheets: Array(String) | out_Config: Dictionary | Done | Done | Done
Close Edge Browser | Yes | Not Required
Prompt user for input file Renamed as: BrowseFile | Yes | Yes | 4 | in_ConfigFile:Dictionary | out_strFilePathInvoices:string | Done | Done | Done | 2022-05-05 | 2022-05-05 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | To adjust form display size To add additional configurable parameters
Read input file | Yes | Yes | 4 | 1. in_Config : Dictionary 2. in_strInputFilePathInvoices: String | out_dtMainDataInvoices: Datatable | Done | Done | Done | 2022-05-06 | 2022-02-07 | Yes | Yes | yes | yes | Yes | Yes | Yes | Yes | Yes | To rename variables
Validate input file | Yes | Yes | 8 | 1. In_config 2. Io_dtMainDataInvoices | NA | Done | Done | Done | 2022-05-09 | 2022-05-10 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | To validate data in columns - Invoice amount, Invoice Date, GL Date &Terms date
Launch Oracle ERP | No | NA | 2 | 1. In_Config | NA | Done | Done | Done | 2022-05-09 | 2022-05-17 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Login to Oracle ERP | No | NA | 8 | 1.in_Config: Dictionary | NA | Done | Done | Done | 2022-05-06 | 2022-05-16 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | To add login success validation To add retry logic for login failure
Login Page | No | NA |  | 1.in_Config: Dictionary | NA | Done | Done | Done | 2022-05-06 | 2022-05-16 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Navigate to Invoices | No | NA | 4 | 1.in_Config: Dictionary 2.in_Responsibility:String | NA | Done | Done |  | 2022-05-06 | [10 empty] | To add logic for DOL payables manager validation
Handle security warnings | Yes | Yes | 16 | 1. in_Config:Dictionary | NA | Done | Done |  | 2022-05-06 | [10 empty] | To add logic to handle all prompts dynamically
Open Invoice Workbench | No | NA | 2 | 1.in_Config:Dictionary | NA | Done | Done |  | 2022-05-15 | 2022-05-19 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Enter Invoice details in Master Block | No | NA | 24 |  | NA | Done | Done |  | 2022-05-13 | [10 empty] | 1. To enter 12 fields (Type, PO number, Supplier site, Invoice date, Invoice number, Invoice amount, GL Date, Payment currency, Terms date, Terms, Payment method, Pay Group) 2. To validate 10 fields for exceptions (Type, PO number, Supplier site, Invoice date, Invoice number, GL Date, Payment currency, Terms, Payment method, Pay Group) 3. To add status in excel for relevant exceptions 4. To add retry logic wherever necessary (TBD)
Delete Invoice | No | NA | 4 | 1.in_Config:Dictionary |  | Done | Done |  | 2022-05-15
Enter Invoice details in Detail Block | No | NA | 24 | [16 empty] | 1. Find PO window -3 UI interactions, 1 validation 2. Match to PO window- 4 UI interactions, 1 validation 3. Invoice Workbench- 1 UI interaction 4. Invoice Actions- 2 UI interactions 5. Invoice Workbench-2 validations 6. To add status in excel for relevant exceptions 7. To add retry logic wherever necessary (TBD)
Update status in Output file | Yes | Yes | 4 | [16 empty] | To update Bot status and Bot comments along with exceptions
Send mail to SME | Yes | Yes | 4 | [16 empty] | To remove message box logic
Logout Oracle ERP | Yes | Not Required
Custom RE Framework | Yes | Yes | 4 | [16 empty] | To remove Journal references

## Sheet4
Done
hardcode